## Product Backlog
Item | Type | Size/Estimated | Priority
View menu (Foods & Beverage) | Features | 2 | 1
Manage menu item (food & beverage) (name & price) | Features | 4 | 2
View picture of menu | Features | 1 | 3
Manage item picture | Features | 2 | 4
View ingredients of menu item | Features | 1 | 5
Manage menu ingredients | Features | 2 | 6
View menu item duration | Features | 1 | 7
Manage item duration | Features | 2 | 8
Order menu | Features | 2 | 9
View customers order by table number | Features | 1 | 10
View bill | Features | 1 | 11
Request bill | Features | 1 | 12
View customers bill request | Features | 1 | 13
Print bill | Features | 2 | 14
View order status | Features | 1 | 15
View item requests to be cooked | Features | 1 | 16
Update item request status | Features | 1 | 17
Add review | Features | 2 | 18
View customers' review on item | Features | 1 | 19
View customers' review on restaurant | Features | 1 | 20
View total sales | Features | 2 | 21
View favourites item | Features | 2 | 22
View ingredients stock | Features | 1 | 23
View low stock of ingredients | Features | 1 | 24
View ingredients stock detail with expired date | Features | 2 | 25
View menu item ingredients detail for cooking | Features | 1 | 26
View menu item cooking recipe (step by step) | Features | 1 | 27
Manage cooking recipes | Features | 4 | 28

## Sprint Backlog Features 1 & 2
Team Name | NIM | Initial
Nazira Andjani | 1801414214 | NA
Avini Fazrie | 1801377194 | AF
Vinzen Ferryl Yuwanto | 1801392251 | VF
Fadhilah Dirayati | 1801391343 | FD
Astrid Nadia | 1801400606 | AN
Febrian Vingky | 1801384205 | FV
Jachinta Tanujaya | 1801381235 | JT
Abraham Kitlaw Ginting | 1801410304 | AG
Alvin Kristanto | 1801383726 | AK
Denis Adinata | 1801384836 | DA
Features 1 : View menu (Foods & Beverage)
Task Name | Duration (hours) | PIC | hours | nb :
HTML Mockup | 7 | AK,FV | 7 | bikin HTMLnya
Code the UI | 5 | AN | 5
Icon & CSS design | 14 | FD,DA | 14
Code the service | 7 | JT | 7 | ambil data dari databasenya, ya select select gitu
Test scenario for UI | 9 | NA | 9
Test scenario for service | 7 | AG | 7
Design the table | 9 | VF | 9 | desain tabelnya(atributnya ada apa aja)
Code the table imigration | 5 | AF | 5 | create tabel ke laravel. entah apa ini(?)
|  | Total | 63
Features 2 : Manage menu item (Foods & Beverage) (Name & Price)
Task Name | Duration (hours) | PIC | hours
HTML Mockup | 7 | AK,FV | 7
Code the UI | 5 | AN | 5
Icon & CSS design | 14 | FD,DA | 14
Code the service | 7 | JT | 7
Test scenario for UI | 9 | NA | 9
Test scenario for service | 7 | AG | 7
Design the table | 9 | VF | 9
Code the table imigration | 5 | AF | 5
|  | Total | 63
Function : Manipulation create, insert, remove, manipulation data